## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2022-01-12
Group Number |  | 1
Participant 1 |  | Saifee Mohammad Farhan
Participant 2 |  | Awan Malik
Participant 3 |  | Tomanovic Pavle
Participant 4
Participant 5
Mentor |  | Prof. Aichbauer Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Tasks in Command Line einbauen | 8 | 10 | 2 | 1
2 | PW-Rücksetzung per Mail | 3 | 8 | 5 |  | 1 | Password wird nicht gehasht eingespeichert, wenn man sich einloggen will; 70/80% Fertig
0
2 |  |  |  | 7 | 1 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol