## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 17.05.2022, 20:00
Group Number |  | 1
Participant 1 |  | Saifee
Participant 2 |  | Tomanovic
Participant 3 |  | Koller
Participant 4 |  | Grassl
Participant 5 |  | Bajraktari
Mentor |  | Prof. Aichbauer Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | WebDesign (NavMenu) | 4 | 5 | 1 | 1
2 | Progress & Highscore | 5 | 5 | 0 | 1
3 | WIKI Page | 6 | 0 | -6 |  | 1
4 | Challenge 2 in Terminal | 7 | 7 | 0 | 1
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -5 | 3 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol