## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 22.11.2022, 17:00
Group Number |  | 1
Participant 1 |  | Saifee
Participant 2 |  | Tomanovic
Participant 3 |  | Koller
Participant 4 |  | Grassl
Participant 5 |  | Bajraktari
Mentor |  | Prof. Aichbauer Lukas
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Problembehebung zu XAMPP | 2 | 2 | 0 | 1 |  | Saifee (Couldn't open)
2 | Edit Trello-Board | 0.5 | 0.5 | 0 | 1 |  | Saifee (updated board)
3 | Recherche zu HighscorePage | 1 | 0 | -1 |  | 1 | Saifee (nicht ausgegangen)
4 | System Documentation | 10 | 4 | -6 | 1 |  | Bajraktari
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -7 | 3 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol