## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2021-12-15 20:30
Group Number |  | 1
Participant 1 |  | Malik Awan
Participant 2 |  | Farhan Saifee
Participant 3 |  | Pavle Tomanovic
Participant 4 |  | Tarek Hitalani
Participant 5
Mentor |  | Prof. Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Einbau von Terminal Fenster | 5 | 4 | -1 | x
2 | Einbau von unterschiedlichen Challenges | 3 | 3 | 0 |  | x | noch nicht funktionsfähig.
3 | Planung von besseren Register-Design | 2 | 2 | 0 | x
4 | Umänderung von Git-Auth0 auf Angular statt ReactJS | 1 | 1 | 0 |  | x | noch nicht komplett eingebaut, ReactJS wurde wegen kompatibilitäts problemen nicht verwendet.
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -1 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol